## Tasks and Timeline
Sauce & Spoon Project Plan
| Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[8 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[8 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Milestone: Tablets received
| Generate quotes and review costs |  |  |  | 14 | bar: WEEK 1 M to WEEK 3 R
| Create contracts and statements of work for vendors | Use past contracts for boilerplate |  |  | 5 | bar: WEEK 2 F to WEEK 3 R
| Order tablets | Shipping updated to ~10 days |  |  | 10 | bar: WEEK 1 R to WEEK 3 W
2 | Milestone: Training complete
| Manager training planning |  |  |  | 5 | bar: WEEK 4 M to WEEK 4 F
| Manager training | One day event |  |  | 1 | bar: WEEK 5 M
| GM meeting with staff regarding buy-in | Let Gilly plan this |  |  | 1 | bar: WEEK 5 T
| Waitstaff training planning |  |  |  | 5 | bar: WEEK 5 W to WEEK 6 T
| Waitstaff training | One day event |  |  | 1 | bar: WEEK 6 W
3 | Milestone: Tablet installation complete
| Book an electrician to install the tablets/wiring | Reference from Deanna |  |  | 8 | bar: WEEK 6 R to WEEK 8 M
| Install working tablets in the bar area at the Downtown restaurant locations |  |  |  | 1 | bar: WEEK 8 T
| Install working tablets in the bar area at the North restaurant locations |  |  |  | 1 | bar: WEEK 8 T
| Sync tablet software with POS | Need to update the POS system |  |  | 7 | bar: WEEK 8 W to WEEK 10 T
4 | Milestone: Launch Day complete
| Create a launch day plan: staffing, troubleshooting, etc. |  |  |  | 20 | bar: WEEK 8 R to WEEK 12 W
| Upload branding to tablets | Connect the marketing team to Terrific Tablets |  |  | 10 | bar: WEEK 10 T to WEEK 12 M
| Load menus into the tablets | Waiting on Carter |  |  | 7 | bar: WEEK 9 F to WEEK 11 M
| Include messaging about payment security on the tablet | Uploading text |  |  | 1 | bar: WEEK 11 T
| Create a behind-the-scenes video of the scratch-to-table process to show on the tablets |  |  |  | 14 | bar: WEEK 9 F to WEEK 11 F
| Create a procedure for securing tablets at the end of the night (at the table or in a safe) |  |  |  | 13 | bar: WEEK 10 M to WEEK 11 F
| Create and implement a post-dining survey to assess customer satisfaction |  |  |  | 3 | bar: WEEK 11 W to WEEK 11 F
| Test run planning |  |  |  | 10 | bar: WEEK 10 R to WEEK 12 W
| Test run | One day event |  |  | 1 | bar: WEEK 12 R
| Launch day | One day event |  |  | 1 | bar: WEEK 12 F

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Milestone: Tablets received
Generate quotes and review costs
Create contracts and statements of work for vendors | Use past contracts for boilerplate
Order tablets | Shipping updated to ~10 days | 10 days | 5 days | 7 days | 12 days | H
Milestone: Training complete
Manager training planning
Manager training | One day event | 1 | 1 | 1 | 3 | M
GM meeting with staff regarding buy-in | Let Gilly plan this | ? | ? | ? | ?
Waitstaff training planning
Waitstaff training | One day event
Milestone: Tablet installation complete
Book an electrician to install the tablets/wiring | Reference from Deanna | 2 | 1 day | 2 | 3 | L
Install working tablets in the bar area at the Downtown restaurant locations
Install working tablets in the bar area at the North restaurant locations
Sync tablet software with POS | Need to update the POS system | 2 days | 4 hours | 1 day | 3 days | L
Milestone: Launch Day complete
Create a launch day plan: staffing, troubleshooting, etc.
Upload branding to tablets | Connect the marketing team to Terrific Tablets | ? | ? | ? | ?
Load menus into the tablets | Waiting on Carter | 10 days | 3 days | 7 days | 14 days | L
Include messaging about payment security on the tablet | Uploading text
Create a behind-the-scenes video of the scratch-to-table process to show on the tablets
Create a procedure for securing tablets at the end of the night (at the table or in a safe)
Create and implement a post-dining survey to assess customer satisfaction
Test run planning |  | 4 | 2 | 4 | 7 | M
Test run | One day event | 1 | 1 | 1 | 4 | M
Launch day | One day event

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Creating a tablet menu for your resturaunt | https://www.ckitchen.com/blog/2018/7/creating-a-tablet-menu-for-your-restaurant.html | 2025-05-20 | Itemized list of tasks for integrating a tablet menu system
Resturaunt Tablet Best Practices: The Top Ways to Use Tablets in Resturaunts | https://www.cuboh.com/blog/restaurant-tablet-best-practices | 2025-05-20 | Tells you what you can do with the tablet. Gives suggestions
Resturaunt Tablet Implementation Plan | https://www.posmotto.com/blog/restaurant-tablet-implementation-plan | 2025-05-20 | Gives a six step processs for implementing new tablets

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Customer Satisfaction | Table turn time: average < 30 minutes | What is the average table turn time? By how many minutes did the average table turn time change? | Average Table turn time Change in Average Table turn time | FALSE
Customer satisfaction | Check-out time: >1min | Are customers satisfied with checkout processes? | Customer satisfication | FALSE
Customer Satisfaction | Check out Time: >1 min | What was the average check out time before tablet rollout? What is the average check out time per week during tablet rollout? | average check out time (prior to tablet) average check out time per week | FALSE
Customer Satisfaction | Technical Issues: <5% reported per week | How many tablets had issues per week? Which tablets had issues per week? What percentage customers report techincal difficulties? | Count of tablets with issues per week Tables/seat with defective tablet Percentage customers with tablet issues | FALSE
Customer Satisfaction | Order Accuracy: %100 | How many customers received incorrect orders? What percentage accuracy are the orders? | Count of Incorrect orders Order accuracy percentage | FALSE
Customer Satisfaction | Wait Time: <10 minutes in lobby before seated | How many customers waited 10 minutes or more in the lobby? By what percentage did customers waiting > 10 mintues in the lobby change by? | Customers in lobby more than 10 minutes Percentage customers waiting more than 10 mintues | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Customer Satisfaction | What is the average table turn time? By how many minutes did the average table turn time change? | Table turn time: average < 30 minutes | How long is the average table turn time? | Open-ended
Customer Satisfaction | What is the average table turn time? By how many minutes did the average table turn time change? | Table turn time: average < 30 minutes | How long did your orders take to come? | Multiple choice | less than 10 minutes | 10-15 minutes | 15-20 minutes | 20-25 minutes | 25+ minutes
Customer satisfaction | Are customers satisfied with checkout processes? | Check-out time: >1min | On a scale of 1 (bad) to 5 (great) rate your checkout experience? | Scaled | 1 | 2 | 3 | 4 | 5
Customer Satisfaction | What was the average check out time before tablet rollout? What is the average check out time per week during tablet rollout? | Check out Time: >1 min | How long is the average checkout time prior to tablets launch? | Open-ended
Customer Satisfaction | How many tablets had issues per week? Which tablets had issues per week? What percentage customers report techincal difficulties? | Technical Issues: <5% reported per week | Did your tablet experience technical issues? | Yes/No | Yes | No
Customer Satisfaction | How many tablets had issues per week? Which tablets had issues per week? What percentage customers report techincal difficulties? | Technical Issues: <5% reported per week | One a scale of 1 (hard) to 5 (easy), how difficult was it to understand how to use the tablets? | Scaled | 1 | 2 | 3 | 4 | 5
Customer Satisfaction | How many customers received incorrect orders? What percentage accuracy are the orders? | Order Accuracy: %100 | Did your receive any incorrect orders? | Yes/No | Yes | No
Customer Satisfaction | How many customers waited 10 minutes or more in the lobby? By what percentage did customers waiting > 10 mintues in the lobby change by? | Wait Time: <10 minutes in lobby before seated | You waited more than 10 minutes in the lobby before seated | True/False | TRUE | FALSE
Customer Satisfaction | Would we get more customers by implementing the tablet system? | Likelyhood to recommend to a freind | Would you recommend this resturant to a friend | Yes/No | Yes | No