## Retrospective Ideas
Feedback From: | Type: | Description: | Evidence: | Actions:
Customers | Went well | Tablet experience was good | 40% thought tablet experience was good, 32% thought it was great. | Continue tablet use
Customers | Went well | tablet navigation was mostly easy | 78% of people thought tablet navigation was neutral to easy | Find ways to make tablet navigation even easier
Customers | Went well | Ordering from tablet menu was easy | 74% of people thought it was neutral to easy to order directly from the tablet | Make it easier to order from the tablet, move more percentage from hard to neutral over
Project team | Went well | Punctuality | Alex - The food came out on time"
Customers | Went well | New letter sign up | 78% of customers signed up for newsletters
Project team | Went well
Project team | Needs improvement | Food Order Accuracy | Larissa - "Yes, we noticed that as well. Not as many as before, but there were still some food orders that got sent back." | Address potential technical issues for low ticket accuracy
Project team | Needs improvement | Kitchen Speed | Zame - "we’d like to do a bit more to help the back of house staff scale up their operations before the main launch. We want everyone to be prepared to handle a larger volume of orders." | Train and hire to handle larger volumes of orders
Project team | Needs improvement | Tablet Implementation | Seydou - "There was some vacation time that was unaccounted for, so this is a good reminder to make sure we plan things properly based on everyone’s availability." | Have better accountability for workers