|  | Closeout Report: Tablet Rollout` |
| --- | --- |

# Project Summary

Launch table tablet menus at North and Downtown locations to improve restaurant efficiency and customer experience.

# Methodology

- Use waterfall method for installing all the tablets and getting the updated menu, then used Agile to put the menu into the tablet software

# Results

Performance Baseline:

|  | Planned | Actual | Notes |
| --- | --- | --- | --- |
| Actual Project Schedule vs Planned | Launch on Apr. 23 | Launched on Apr. 23 | We were able to launch on the day we wanted, but had to accelerate our tasks due to delays |
| Actual Project Cost vs Planned | Training materials and fees: $10,000 Hardware and software implementation across locations: $3,500 Maintenance (IT fees): $5,000 Updated website and menu design fee: $5,000 Other customization fees: $550 | Training materials and fees: $7,486 Hardware and software implementation across locations: $3,600 annually Maintenance (IT fees): $0 (included with hardware order subscription) Updated website and menu design fee: $4,250 Other customization fees: $578 | Overall, we nearly matched our budget |
| Planned Scope vs Delivered Scope | Install tablets at two restaurant locations Launch at the beginning of Q2 (April 1) Create a plan for how to train staff on the new system | Physically installed tablets at two restaurant locations via electrician Added menus, coupons, branding, and additional content to tablets Integrated tablets with POS system Negotiated with tablet vendor over timing Created a plan for training Managed waitstaff expectations and concerns Trained BOH and FOH Created system for maintenance/locking Implemented system of surveying and measuring customer satisfaction | We didn’t realize how many moving pieces we were going to encounter |

Key Accomplishments:

- North and Downtown locations returned table turn time by 30 minutes

- Downtown location experienced 20% increased guest count (10% greater than initial goal)

- Food waste reduced by 25% as wanted

# Lessons Learned

- Still issues with wrong orders and coordinating with Carter about addressing issues in the kitchen staff

- Use a pre-service testing checklist to weed out any glitchy tablets.

- Simplified tablet navigation

# Next Steps

- Copy same system to the other locations

- Continue to improve order accuracy

- Continue to survey and solicit feedback from guests

# Project Documentation Archive

- [link the project proposal]

- [link the project charter]

- [link the project plan]

- [link the evaluation findings presentation]