## Slide 1
Stakeholder | Role | Power (H/M/L) | Interest (H/M/L) | Notes
Omar Mubarak | Owner/Project Sponsor | H | L | Very busy schedule. Maintains overall vision. Not in the details
Peta Tsosie | Project Manager | M | M | This is me in this scenario
Deanna Coleman | Director of Operations | H | H | Responsible for comms and restaurant integrity
Carter Ward | Executive Chef | M | H | FInal say on menu choices
Gilly Tyson | General Manager (North Location) | M | H | 
Alex Schmidt | General Manager (Downtown Location) | M | H | 
Nia Williams | General Manager (Waterfront) | M | L | Nothing to do with current project
Zane Dutchman | Kitchen Manager | L | M | 
Larissa Stein | Kitchen Manager | L | M | 
Seydou Diallo | Restaurant Technology Consultant | L | M | 
Stakeholder Analysis

## Slide 2
Keep satisfied (high priority)
Manage closely (high effort)
Monitor (minimum effort)
Show consideration
Power
high
low
med
high
low
Omar
Owner
Drag each stakeholder’s box to the appropriate place on the power-interest grid
Deanna
Director of Operations
Carter
Exec. Chef
Gilly
GM - North
Alex
GM - Downtown
Zane
Kitchen Manager - North
Larissa
Kitchen Manager - Downtown
Seydou
Restaurant Consultant
Interest
med
Nia
General Manager - Waterfront